## Work order log
Hotel work order log
One line per request, in the order they arrive. Read every open line each morning: no owner gets one, past target gets a decision.
No. | Reported (date and time) | Room or place | What is wrong | Reported by | Guest affected (Y/N) | Priority | Target time | Out of order (Y/N) | Assigned to | Started | Done | Time spent | Parts used | Closed by | Close note
0412 | Mon 9:40 AM | 214 | Shower drips after closing | Maria, housekeeping | Y | Normal | Mon 9:40 PM | N | Victor | Mon 1:40 PM | Mon 2:15 PM | 35 min | Shower cartridge x1 | Victor | Replaced cartridge, tested hot and cold
0413 | Mon 10:05 AM | 305 | AC running but blowing warm air, guest in room until 2 PM | Front desk | Y | High | Mon 12:05 PM | N | Phil | Mon 10:40 AM | Mon 11:20 AM | 40 min |  | Phil | Cleared blocked drain, cleaned filter, cooling tested 10 min
0414 | Mon 11:30 AM | Lobby | Two downlights out by the lifts | Night auditor | N | Low | Thu 11:30 AM | N | Victor
From https://turndownhq.com/guides/hotel-work-order-template/ . Free to copy and use at your property.

## Work order form
Hotel work order log
Print one per job. File by number when closed.
Field | Fill in
Number
Room or place
What is wrong
Reported by, date and time
Guest affected (yes or no, until when)
Priority (urgent, high, normal, low)
Done by (date and time)
Room out of order (yes or no)
Assigned to
Started
Parts used
Time spent
What was done
Closed by, date and time
Room released to the front desk (time and initials)
From https://turndownhq.com/guides/hotel-work-order-template/ . Free to copy and use at your property.

## Priorities
Hotel work order log
Example targets. Change them to your own and agree them with the front desk.
Priority | Use it when | Examples | Target
Urgent | Safety risk, or damage spreading now. | Water through a ceiling, a guest stuck in the elevator, a door that won't lock, sparks at a socket. | 30 minutes
High | A guest can't use the room properly, or an arrival depends on it. | AC not cooling with a guest in the room, no hot water, a toilet that won't flush. | 2 hours
Normal | Guests would notice, but the room still works. | A dripping tap, a stiff balcony door, one bulb out by the bed. | 12 hours
Low | Back of house or cosmetic, no guest impact today. | Paint touch-up in a corridor, a loose shelf in the linen room. | 3 days
From https://turndownhq.com/guides/hotel-work-order-template/ . Free to copy and use at your property.